## Slide 1: Fitness for Service Software Version 3.0 REPCO -Orange Technology 21-08-2017

## Slide 2: Project status
Latest updated | 19th August 2017 |  |  |  |  |  |  |  |  |  |  | 
 |  |  | August |  |  |  |  | September |  |  |  | 
Modules | Status | Target | w1 | w2 | w3 | w4 | w5 | w1 | w2 | w3 | w4 | 
Brittle Frature | Validating (target - done in wk4) | Aug / w4 |  |  |  |  |  |  |  |  |  | 
Pitting Corrosion | done - waiting for validation | Aug / w5 |  |  |  |  |  |  |  |  |  | 
Weld Misalignment | done - waiting for validation | Aug / w5 |  |  |  |  |  |  |  |  |  | 
Dent-Guage Combination | done - waiting for validation | Aug / w5 |  |  |  |  |  |  |  |  |  | 
Local Metal Loss | In progress 50% | Sep / w1 |  |  |  |  |  |  |  |  |  | 
Genetal Metal Loss | In progress 50% | Sep / w1 |  |  |  |  |  |  |  |  |  | 
Hydrogen Damage | pending | Sep / w1 |  |  |  |  |  |  |  |  |  | 
Crack-like flaw | pending | Sep / w1 |  |  |  |  |  |  |  |  |  | 
Creep rupture | pending | Sep / w2 |  |  |  |  |  |  |  |  |  | 
Fire Damage | pending | Sep / w2 |  |  |  |  |  |  |  |  |  | 
Lamination | pending | Sep / w2 |  |  |  |  |  |  |  |  |  | 
** This plan is not included billing lead time condition. |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | = Orange delivered to SCG |  |  |  |  |  |  |  | 
 |  |  |  | = SCG validation/feedbacks |  |  |  |  |  |  |  |